## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Any other metrics defined in your SPPP
0 | 09/05-09/12 | - Inital project decision | - N/A | - Difficulty in key application decisions | - Prior research | 0 | 0 | 0 | 0 | 0 | 51.8 | 33.3 | 18.5 | 11 | 8 | 0 | 3.6 | 0.1 | 6.5 | 4.1 | 6
1 | 09/12-09/25 | - Basic UI flow - Dockerization of webapp & database - Near full transaction functionality - Secure password hashing and storage | - Database consistency - Packaging JSP pages - User session management | - Miscommunication of assignments - Miscommunication of updating documentation | - More usage of JIRA for progress and assignment | 3 | 5 | 3 | 1 | 2 | 221 | 165 | 56 | 37.5 | 32 | 9 | 33 | 21 | 25.5 | 7 | 18.5
2 | 09/26-10/10 | - Inclusion of JWT tokens - Export transactions - Display of transaction history | - Leveraging JWT tokens - API design - Test coverage | - Other work obligations | - Continued progress on the | 13 | 8 | 2 | 1 | 2 | 220.5 | 176 | 44.5 | 29 | 21.5 | 6 | 79 | 18 | 16 | 6.5 | 23.5
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## William Aftring
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 5 | 3 | 2 | 0 - Learn Springboot 1 - Risk analysis 5 - JIRA Administration 7 - SPPP report work | 1 | 0.5 |  | 0.5 |  |  |  | 1 | 1. Wrote 2 sections of SPPP 2.
2 | 09/12-09/18 | 0
3 | 09/19-09/25 | 27.5 | 25 | 2.5 | 0 - Dockerizing application 1 - Working with Hanwen on sec development 2 - SDD Review 3 - STD Review | 7 | 3 |  | 7 | 1 | 2 | 4 | 1 | 1. Dockerized database and web application 2. Collaborated on registration + login functionality 3. Researched token management options 4. Created knowledge transfer on containers & network traces | - Familiarity with springboot - Database consistency - Project setup - Maven familiarity | - Learned more through usage - Normalized this through the .sql file - IDE now manages this | - Continue session management | 15h
4 | 09/26-10/03 | 28.5 | 26 | 2.5 | 0 - JWT learning 3 - Implementing JWT 5 - General communications admin | 2 |  |  | 22 |  | 2 |  |  | 1. Initial JWT development | - I don't understand JWT - I don't understand Springboot - I don't like the web | - Read more on the topics | - Continue on JWT work | 20h
5 | 10/04-10/10 | 29.5 | 27 | 2.5 | 2 - Updating API design 3 - JWT Implementation 6 - Server deployment setup | 0 |  | 2 | 20 |  |  | 5 |  | 1. Completion of JWT development 2. Start of server deployment 3. Deployment teachings | - Under provisioned VM | - Upgrade VM deployment | - Complete server deployment - Implement logout | 15h

## Maryam Hussein
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
| 09/05-09/12 | 2.5 | 0 | 2.5 | #Task 0: Create a Jira dashboard for team tracking. # Task 1: Perform risk analysis for the Design and Implementation section. # Task 2: Attend a group meeting # Task 3: Set up Git and GitHubDesktop # Task 4: Set up IntelliJ as the integrated development environment (IDE). # Task 8: Finish and submit lab 1. #Task9: done with the management plan | [8 empty] | setup the Jira Borad for tracking our work for team write down the Mangment Plan discuess with team and suggest ideas for project | no issues
| 09/12-09/18 | 12.5 | 10 | 2.5 | #completed the Software Design Document (SDD) and designed both the user interface (UI) and backend components for our project.# #reating a well-defined design pattern and architecture for our team, which includes establishing the database structure. #initiated the development of our Spring Boot application, laying the foundation for the backend. #added necessary configurations to our application and created a structured directory tree for our project. #ensure the smooth functioning of our application, I've included all essential dependencies and made the necessary connections between the backend and frontend. "#I've pulled the latest code changes from our team's repository and performed thorough manual testing using tools like Postman and the UI. " |  | 2 | 2 | 1 | 3 | 1 | 1 |  |  | no issues
| 09/19-09/25 | 2.5 | 0 | 2.5 | #completed the Software Design Document (SDD) and designed both the user interface (UI) and backend components for our project.# #reating a well-defined design pattern and architecture for our team, which includes establishing the database structure. #initiated the development of our Spring Boot application, laying the foundation for the backend. #added necessary configurations to our application and created a structured directory tree for our project. #ensure the smooth functioning of our application, I've included all essential dependencies and made the necessary connections between the backend and frontend. "#I've pulled the latest code changes from our team's repository and performed thorough manual testing using tools like Postman and the UI. | [9 empty] | no issues
| 10/03-10/08 | 16.5 | 14 | 2.5 | Task 0: Focus on the development of the Export Transaction backend. Task 1: Concentrate on creating a frontend button for exporting transaction history. Task 2: Perform reviews and testing for the work completed by other team members. Task 3: Evaluate the design and decide whether to make changes or stick with the current design. |  | 2 | 3 | 2 | 3 | 3 | 1 |  |  | no issue

## Andrew Ouellette
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/11 | 10 | 8 | 2 | 0 - Brush up on Git/Spring/React/Docker/NodeJS 1 - Branching strategy analysis, write configuration section 5 - Group meetings and Discord communitation 6 - Setup Git for projects/labs | 3 | 2 |  |  |  | 2 | 1 |  | 1. Write documentation on configuration plan/strategy. 2. Setup Git branches for future development. | 1. Not expert on Spring or React. 2. Unable to protect main branch. | 1. Research Spring and React further. 2. Research alternatives to protect branch if not able to. | 1. Continue to researh Spring/React to increase current understanding. Potentially reach out to design leader for help. 2. Continue researching how to protect main branch. | 8
2 | 09/12-09/18 | 8 | 6.5 | 1.5 | 0 - More Spring research 1 - Create User stories, acceptance tests 5 - Group meetings | 1 | 4 |  |  |  | 1.5 |  |  | 1. Write user stories and acceptance tests. | 1. Still need to learn more about Spring | 1. Read more about Spring. | 3. Implement code. 4. Test implementation | 10
3 | 09/19-09/25 | 23 | 20 | 3 | 0 - Spring Boot/Docker/JSP 3 - UserServiceTest testing 4 - Review PR and test Pull Requests 5 - Work through issues with team | 4 |  |  | 4 | 8 | 4 |  |  | 1. UnitServiceTest 2. Presentation 3. Complete document requirements | 1. Authentication not complete. | 1. Research JWT and other alternatives. | 0 - Learn about AWT/Spring 3 - AWT Implementation 4 - AWT Test | 12
4 | 09/26-10/02 | 5.5 | 4 | 1.5 | 0 - JSP/Spring Boot 1 - Review and choose user story to implement 5 - Group meetings | 3 | 1 |  |  |  | 1.5 |  |  | 1. Delegate user stories. | N/A | N/A | 3. Implement code for user story 4. Test implementation | 12
5 | 10/03-10/09 | 20 | 16 | 4 | 0 - JSP 3 - Implement BudgetGoal feature 4 - Test implementation 5 - Work through PR and merge conflicts | 3 |  |  | 10 | 3 | 4 |  |  | 1. Implement BudgetGoal feature. | 1. "Current Amount" column on page still needs to be implemented. | 1. Research solutions and reach out to team if unable to solve for help. | 0 - Research JSP further 3 - Add BudgetGoal "CurrentAmount" column. 4 - Write up unit tests for code created. 6 - Implement CI/CD for project | 18
6 | 10/10-10/17
7 | 10/17-10/21

## Christan Pratt
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/5 - 9/11 | 17 | 11 | 6 | 0 - learn git, read requirements analysis sections in textbook and slides, begin to familiarize myself with spring boot with youtube tutorial 1 - define and document high level requirements, identify risk related to requirements 5 - team meeting held, and discord communications 6 - used git to update team.md 7 - create powerpoint presentation template | 5 | 2 |  |  |  | 2.5 | 0.5 | 1 | 1. Write the requirements of SPPP 2. Update the risk and management related of the SPPP_RiskManagement 3. Created the powerpoint presentation template 4. Update Progress Report | 1. Challenge with git commit, separating the save to stage and push to repo using the IDE 2. Time constraints due to previous obligations | 1. Used IDE in combination with Github desktop, will change settings from never push to both now that initial assignment which appeared to require them be separated tasks was completed 2. With the cadence agreed with the group members, the expectation is to schedule future activities around them | 0 - continue to learn spring boot and requirement analysis techniques 1 - define detail level requirements 3 - support the implementation team 5 - team meeting and consistent discord communication | 8
2 | 09/12-09/18 | 12 | 9 | 3 | 0 - review module 1 and 2 to prepare for quiz; continue to research on the spring boot application 1 - initial read about Pivot Tracker for creating user stories, then had to pivot to Jira to learn how to do since team was using jira | 6 | 3 | [6 empty] | 1. Created User Stories for Lab2, which by extension was required for the team project | 1. Prior commitments made this week challenging and it was important to fit in the study wherever possible. | 1. Although difficult, my committee level remained high and contributed my best for individual and team success, kept engaged where possible and communicated often; team members also assisted | 0 - continue to learn spring boot, start to understand unit testing implementation 2 - support the team with SDD documentation 3 - support the team with implementation of design components 5 - scheduled meetings and standups | 12
3 | 09/19-09/25 | 30.5 | 15.5 | 15 | 0 - spring boot postmapping and getmapping, mockito unit testing, git branch management 2 - contributions to the SDD 3 - contributions to the implementation of features 4 - contributions to the testing of features and the STD 5 - team meeting and consistent discord; training opportunities and content sharing | 5 |  | 2.5 | 6 | 2 |  |  |  | 1. Update business logic section of SDD 2. Update database design section of SDD based on redesign, inclusive of entity relationship diagram 3. Create Initial database design sql scripts 4. Create Initial Postman Workspace\Collection and API Request 5. Implement Model classes based on database design 6. Implement Transaction Expenses related features and Get Transaction by Type feature 7. Manual Test and Unit Test Transaction Expense related features and Get Transaction by Type feature 8. Create Manual Testing Template and attached to STD | 1. Learning curve to implementation using frameworks 2. Model design changes increased the time (cost) 3. The team ability to move subtasks in Jira, and my inconsistency in updating. | 1. We used a pair programming approach, that allowed the team to review code implementation at the same time, also it gave us an opportunity to discuss approaches and industry best practices 2. The team initial created the models based of the SDD, but decision to rework model from Income and Expense to a transaction was made. During pair programming, it was discussed, but we continued with the initial design. Learning experience to not be afraid to speak up, as we saw the cost of rework in action. 3. The team has updated the backlogs in time for iteration, but I would like to be more conscious of updating in a more timely manner. | 0 - learning JWT token and security features, JSP concepts; review modules 3,4 for quiz 3 - implementation of features once security is fully implemented; and UI 4 - testing of features | 12
4 | 09/26-10/02 | 14 | 10 | 4 | 0 - jwt security with springboot, review module 3 and 4 to prepare for quiz/lab 3 - implement deleteTransaction feature for lab3 4 - implement unit Testing for deleteTransaction feature for lab3 5 - team meeting and consistent discord | 5 |  |  | 1 | 3 | 1 |  |  | 1. Create New Sprint and Add Requirements (use stories) 2. Meeting Minutes | No Issues | No Issues | This week was fairly light compared, as persons prepared for quiz and lab. Anticipates that it will ramp up quickly to refactor features and unit test implementations. Team has to validate security implementation and modify existing implementations to accomodate security context.
5 | 10/03-10/09 | 22.5 | 14.5 | 8 | 0 - JSP, jQuery and ajax api calls 1 - review features and discuss new for iteration, update SPPP 3 - refactor deleteTransaction feature to include business logic, add front end interface, update existing features to test security implementation 4 - create unit test for deleteTransaction feature, review PR with Whitney/Andrew for test main 5 - team meeting and consistent discord, update documentation 6 - update postman collection to inherit JWT Token for each request | 2 | 1 |  | 5 | 2 | 4 | 0.5 |  | 1. Update database design section of SDD based on budget goals and comments, inclusive of entity relationship diagram 2. Updated Initial Postman Workspace\Collection and API Request to include JWT Token 3. Implement View Transaction History Feature and Unit Test 4. Implement Delete Transaction feature and Unit Test 5. Manual Test and Unit Test Register, Login, Add Transactions, Delete Transaction, Transaction History features using Postman and updated the Manual Testing Template attached to STD 6. Update Readme to include API Endpoints 7. Update Presentation | No Issues | No Issues | Refactor solution to improve readability and maintainability. Retest and address any minor issues identified. Prepare for deployment. Start exam preparation. | 12
6 | 10/10-10/17 | 0 | 0 | 0
7 | 10/17-10/21 | 0 | 0 | 0

## Whitney To
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05/-09/12 | 4.8 | 2.8 | 2 | 1 - work on SPPP and Presentation slides 3 - finish lab 1 4 - check gitHub if changes were pushed 5 - 6 - setup git / intelliJ | 0 | 2.5 | 0 | 0.1 | 0.1 | 0 | 0.1 | 0 | 1 - Write up the QA Planning in SPPP and add info on the presentation slides 3 - write up the lab1 report and submit 4 - check gitHub if changes were pushed 5 - 6 - set up git/intelliJ, add introduction on team.md , then commit and push the changes with git | - | - | - | -
2 | 09/12-09/18 | 24.5 | 21.5 | 3 | 0 - JSP, Docker 1 - User stories 2 - Db design change 3 - income transaction related tasks 4 - automation and manual testing 5 - pair programming 6 - 7 - finish lab2 and quiz1 | 0.5 | 1 | 1 | 6 | 4 | 8 | 0 | 1 | 0 - read over JSP files and understand how to work with JSP to make UI components and connect to backend 2 - refactor add income logic to account for the DB change 1 - create userstories and their sub tasks for functionality 3 - implemented controller/service/persistence logic for transaction related to income, connect to front end for full flow 4 - created unit tests for methods, touched on integration test but havent finished 5 - pair programming to go over what to done, how to implment income/expense functionality and carry out actual implementation together 7 - finish lab2 with the user stories and quiz1 | 1. issue with integration implementation | 1. continue researching for the correct configuration and fix any error and include integration test for main applicaiton in next iteration | 1.1 research configuration 1.2 implement tests without mocking dependency | 1.1 - research : 2 hours 1.2 - implemtation and testing : 4 hours (to cover for previous iteration's methods as well)
3 | 09/19-09/25 | 5.5 | 4 | 1.5 | 4 - manual test, integration test 7 - work on documents | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 4 - compelete manual tests for user login, registration, get user balance and include all test result in the the STD report 7 - work on documents for this iteration such as STD, reviewing SDD, complete personal task on progress report, review other files | incomplete catching error message and display on UI for transaction action from UI | in next iteration, implement logic in front end to catch error message from request and display message on UI | - implement logic in UI to catch error - make sure backend send appropriate message for API call | 2 hours
4 | 09/26-10/02 | 2 | 2 | 0 | 4 - manual test, integration test | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 4 - added more manual test, integration test to cover previous features | there are pending integartion tests from previous apis created and newly api created for iteration 2 | implement the test cases | implement the test cases | 4 hours
5 | 10/03-10/09 | 24.5 | 20.5 | 4 | 0 - JSP,Docker,Deployment 1 - User Stories 3 - view analytics feature 4 - manual test, integration test 7 - work on documents / presentation | 2 | 0.5 | 0 | 10 | 4 | 0 | 0 | 4 | 4 - compelete manual tests for user login, registration, get user balance and include all test result in the the STD report 7 - work on documents for this iteration such as STD, reviewing SDD, complete personal task on progress report, review other files | no navigation back to dashboard from the analytic page | next iteration will need to add button for this functionality | - add button to navigate back to the dashaboard page | 1 hour
6 | 10/10-10/17
7 | 10/17-10/21

## Hanwen Zhang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/11 | 5 | 3 | 2 | 0 - Learn Java and Springboot 1 - Risk analysis for security section 5 - Group meeting 6 - Setup git and complete lab 1 | 1 | 1 |  |  |  |  | 1 |  | 1. Analyze risk for security on the project and wrote 3 risks 2. Complete lab1 and submit the assignment via blackboard | 1. not proficient with Java and Sprint Boot 2. not familiar with security issues on software | 1. watch tutorials and read docs for Java and Spring boot 2. find relevant materials for security issues in software development | 1. continue to learn Java and Sprint Boot 2. continue to learn secure practice for software development 3. explore how Github Security works | 5
2 | 09/12-09/18 | 12 | 10.5 | 1.5 | 0 - Learn Java and Springboot 0 - Investigate and learn security 1 - Create user stories, acceptance tests, feature tasks 2 - Complete SDD draft for security section 5 - Group meeting 6 - Research on Docker and see how it setup 7 - Complete Lab 2 7 - Complete Quiz 1 | 3 | 2 | 1.5 |  |  |  | 1 | 3 | 1. Analyze user stories/acceptance tests/feature tasks, and wrote 3 user stories on Jira group project board 2. Complete writing the draft on the design document for the security section after research on the topic 3. Complete lab2 and submit the assignment via blackboard 4. Complete quiz1 and submit the assessment via blackboard | 1. not proficient with Java and Sprint Boot 2. not familiar with security issues on software | 1. watch tutorials and read docs for Java and Spring boot 2. find relevant materials for security issues in software development | 1. continue to learn Java and Sprint Boot 2. continue to learn secure practice for software development 3. explore how Github Security works | 12
3 | 09/19-09/25 | 22 | 11 | 11 | 0 - Learn Java development & JWT token 2 - Update SDD for security section 5 - Group meeting 6 - Understand Docker 7 - Work on Project Development | 5 |  | 1 |  |  | 3 | 1 | 12 | 1. Work on user account registration 2. Work on user account authentication | 1. JWT session development | 1. Research and tryout in local development | 1. continue to learn security related software development 2. explore how Github Security works | 15
4 | 09/26-10/02 | 10 | 8 | 2 | 0 - Learn about forget password function 5 - Group meeting 7 - Work on Project Development 7 - Complete Lab 3 7 - Complete Quiz 2 | 4 |  |  |  |  | 2 |  | 4 | 1. Complete lab3 and submit the assignment via blackboard 2. Complete quiz2 and submit the assessment via blackboard | 1. Forget my password functionality for the project | 1. Research and tryout in local development | 1. continue to learn security related software development | 20
5 | 10/03-10/09 | 10 | 8 | 2 | 0 - Learn about forget password function 5 - Group meeting 7 - Work on Project Development | 2 |  |  |  |  | 3 |  | 5 | 1. Completed forget my password functionality for the project 2. Code reviews for the PRs for the project | 1. Forget my password functionality for the project | 1. Research and tryout in local development | 1. continue to learn security related software development | 10
6 | 10/10-10/17 | 0 | 0

## Xin Zhao
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Flex leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/5 - 9/11 | 7.5 | 5.5 | 2 | 0 - Learn git, read requirements analysis sections 3 - Presentation recording 5 - Group meetings and Discord communitation 6 - Setup Git for projects/labs | 1 |  |  | 3 |  | 2 | 1.5 |  | 1.Complete project presentation recording 2. Setup Git branches for future development.
2 | 09/12-09/25 | 30.5 | 24.5 | 6 | 0 - Spring Boot/Docker/JSP 1 - Create User stories, acceptance tests 2 - SDD structure diagram 3- UserServiceTest testing 4 - Review PR and test Pull Requests 5 - Work through issues with team 7 - finish lab2 and quiz1 | 4 | 2 | 1 | 9 | 1 | 4 |  | 3.5 | 1. Write user stories and acceptance tests 2. UnitServiceTest 3. SDD structure diagram 4. Complete document requirements
| 09/25-10/10 | 29 | 26 | 3 | 0 - JSP, jQuery and ajax api calls 3 -Add comment functionality to projects. 5 - team meeting and consistent discord, update documentation 7-finish lab3 and quiz2 | 2 | 15 |  |  |  | 2 |  | 7

## QA Metrics
Metric Name | Description | Iteration 1
KLOC | Measure the size of the code base | 1176
# files | Count the total # of files in the project | 47
# of classes | Quantify the total number of classes used. | 27 java classes, 8 JSP files
# of methods | Quantify the total number of methods/functions used. | 32 java methods
Cyclomatic complexity | Measure the complexity of the codebase, identifying areas that may need refactoring.
Defect rate (defects / KLOC) | Calculate the number of defects found per 1,000 lines of code. | 3 / 1176 * 1000 = 2.6
# of defects | Track the total number of defects reported and resolved. | 3
# test cases | Count the total number of test cases in the test suite. | 28
Test case pass rate | Calculate the percentage of test cases that pass successfully. | 28 / 28 passed
Test class coverage | Measure the percentage of code covered by test cases. | 84%
Test method coverage | Measure the percentage of code covered by test cases. | 75%
Test line coverage | Measure the percentage of code covered by test cases. | 84%
Person hours used | Track the total effort expended in person-hours during the project.
# of user stories completed | Quantify the user stories implemented and marked as completed.