## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## William Aftring
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/05-09/12 | 5 | 3 | 2 | 0 - Learn Springboot 1 - Risk analysis 5 - JIRA Administration 7 - SPPP report work | 1 | 0.5 |  | 0.5 |  |  |  | 1 | 1. Wrote 2 sections of SPPP 2.

## Maryam Hussein
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
| 09/05-09/9 |  |  |  | #Task 0: Create a Jira dashboard for team tracking. | [8 empty] | setup the Jira Borad for tracking our work for team | no issue
| 09/05-09/11 |  |  |  | # Task 1: Perform risk analysis for the Design and Implementation section. | [8 empty] | write down the Mangment Plan
| 09/05-09/11 |  |  |  | # Task 2: Attend a group meeting | [8 empty] | discuess with team and suggest ideas for project
| 09/05-09/11 |  |  |  | # Task 3: Set up Git and GitHubDesktop
| 09/05-09/12 |  |  |  | # Task 4: Set up IntelliJ as the integrated development environment (IDE).
| 09/05-09/12 |  |  |  | # Task 8: Finish and submit lab 1.
| 09/05-09/12 |  |  |  | #Task9: done with the management plan

## Andrew Ouellette
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/05-09/11 | 8 | 6 | 2 | 0 - Brush up on Git/Spring/React/Docker/NodeJS 1 - Branching strategy analysis, write configuration section 5 - Group meetings and Discord communitation 6 - Setup Git for projects/labs | 3 | 2 |  |  |  | 2 | 1 |  | 1. Write documentation on configuration plan/strategy. 2. Setup Git branches for future development. | 1. Not expert on Spring or React. 2. Unable to protect main branch. | 1. Research Spring and React further. 2. Research alternatives to protect branch if not able to. | 1. Continue to researh Spring/React to increase current understanding. Potentially reach out to design leader for help. 2. Continue researching how to protect main branch. | 8
2 | 09/12-09/18
3 | 09/19-09/25
4 | 09/26-10/02
5 | 10/03-10/09
6 | 10/10-10/17
7 | 10/17-10/21

## Christan Pratt
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/5 - 9/11 | 11 | 5 | 6 | 0 - learn git, read requirements analysis sections in textbook and slides, begin to familiarize myself with springboot with youtube tutorial 1 - define and document high level requirements, identify risk related to requirements 5 - team meeting held, and discord communications 6 - used git to update team.md 7 - create powerpoint presentation template | 5 | 2 |  |  |  | 2.5 | 0.5 | 1 | 1. Write the requirements of SPPP 2. Update the risk and management related of the SPPP_RiskManagement 3. Created the powerpoint presentation template 4. Update ProgressReport | 1. Challenge with git commit, seperating the save to stage and push to repo using the IDE 2. Time constraints due to previous obligations | 1. Used IDE in combination with Github desktop, will change settings from never push to both now that initial assignment which appeared to require them be seperated tasks was completed 2. With the cadence agreed with the group members, the expectation is to schedule future activites around them | 0 - continue to learn springboot and requirement analysis techniques 1 - define detail level requirements 3 - support the implementation team 5 - team meeting and consistent discord communication | 8

## Whitney To
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05/-09/12 | 4.8 | 2.8 | 2 | 1 - work on SPPP and Presentation slides 3 - finish lab 1 4 - check gitHub if changes were pushed 5 - group meeting 6 - setup git / intelliJ | - | 2.5 | - | 0.1 | 0.1 | 2 | 0.1 | - | 1 - Write up the QA Planning in SPPP and add info on the presentation slides 3 - write up the lab1 report and submit 4 - check gitHub if changes were pushed 5 - contribute to group discussion about roles allocation, tasks to be done for this week, and idea for the project 6 - set up git/intelliJ, add introduction on team.md , then commit and push the changes with git | - | - | - | -
2 | 09/12-09/18
3 | 09/19-09/25
4 | 09/26-10/02
5 | 10/03-10/09
6 | 10/10-10/17
7 | 10/17-10/21

## Hanwen Zhang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/05-09/11 | 5 | 3 | 2 | 0 - Learn Java and Springboot 1 - Risk analysis for security section 5 - Group meeting 6 - Setup git and complete lab 1 | 1 | 1 |  |  |  | 2 | 1 |  | 1. Analyze risk for security on the project and wrote 3 risks 2. Complete lab1 and submit the assignment via blackboard | 1. not proficient with Java and Sprint Boot 2. not familiar with security issues on software | 1. watch tutorials and read docs for Java and Spring boot 2. find relevant materials for security issues in software development | 1. continue to learn Java and Sprint Boot 2. continue to learn secure practice for software development 3. explore how Github Security works | 5
2 | 09/12-09/18
3 | 09/19-09/25
4 | 09/26-10/02
5 | 10/03-10/09
6 | 10/10-10/17
7 | 10/17-10/21