## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status | Owner Responsible
personel | Loss team members | One or more team members drop the class | 3 | 4 | 4 | 24 | team leader and all members | 2023-10-18 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open | Will
| add new team members | Addition of one or more team members | 2 | 2 | 3 | 48 | team leader and all members | 2023-10-18 | Allocate additional time for ramp up of new team member to ensure ease of contribution | No one added so far | Open | Will
| Lack of motivation or responsibility | Loss of motivation on the project given other responsibilities | 4 | 4 | 4 | 16 | Team leader and all members | 2023-10-18 | Ensure that engineers are not burnt out from work allocated in project. | Evaluating engineer work load | Open | Will
Communication | duplicate work | Unnecessary duplication of work | 2 | 3 | 3 | 36 | Configuration and Design Lead | 2023-10-18 | Ensure that engineers are not duplicating efforts by having clearly assigned deliverables | On-going assignment via JIRA | Open | Will
| worked on wrong components | Incorrect ordering of work | 2 | 2 | 2 | 32 | Team leader and all members | 2023-10-18 | Ensure that engineers are following the assigned deliverables | On-going assignment via JIRA | Open | Will
| useless work | Working on unnecessary features | 1 | 3 | 4 | 60 | Team leader and all members | 2023-10-18 | Ensure that engineers are following the assigned deliverables | On-going assignment via JIRA | Open | Will
| inconsistent work | Engineers are not able to allocate enough time to consistently work on project | 4 | 5 | 5 | 10 | Team leader and all members | 2023-10-18 | Ensure that work items are assigned to meet all engineers available bandwidth for development | Bi-weekly standup meetings to clarify available bandwidth | Open | Will
Requirements | unclear requirements | Challenges with requirements due to multiple ideas combined | 3 | 4 | 5 | 30 | Requirements Leader and Team Leader | 2023-10-18 | Ensure that consistent communication with stakeholders to clarify requirments | The key stakeholders have clarity on their requirments and appreciate the time constraints of each sprint | Open | Chris
| scope creep | Feature set being added despite time constraints | 3 | 3 | 4 | 36 | Requirements Leader and Team Leader | 2023-10-18 | Team Leader will manage the scope with stakeholders, clear estimates should be provided to indicate potential feature add | Essential features, desired features and optional features have been defined, and the team should maintain a clear distinction consistently, which they have done well thus far | Open | Chris
| constant requirements changes | Stakeholders do not know what they want, and typically change their minds | 3 | 4 | 4 | 24 | Requirements Leader and Team Leader | 2023-10-18 | Requirements Leader manages stakeholder ask with market research and consistent communication; Change process should be managed with support of Team Leader | High Level Requirements defined thus far, Detail Level Requirements should refine initial requirements, with focus on ensuring clear understanding of wants | Ongoing | Chris
Management | improper task assignments | Requirements should be traceable and properly assigned | 3 | 3 | 5 | 45 | Team leader and all members | 2023-10-18 | Project Team should identify the strengths and weakness of the team members, and utilize to the best of their knowledge. | The team has grown over the past weeks and have identified members strengths and weakness. Do not see an issue with improper assignment; Committment level is also high to support team members | Closed | Chris
| improper planning | Team members do not adequately plan | 1 | 2 | 2 | 40 | Team leader and all members | 2023-10-18 | With the team recent formation, constant touchpoints, and regular meeting interval | Team meeting held and Action items have been added to Jira, this tool should keep the team honest with planning activites; Persons have appreciation for deadlines and plan adequately | Closed | Chris
| lack of management skills | Team Leads do not have the skills required and maybe afraid to voice their concerns | 1 | 3 | 4 | 60 | Team leader and all members | 2023-10-18 | Team leader can have regular touch points to ensure indivaul team members are comfortable with task assignemnts | Initial leader roles agreed and first set of tasks assigned. Thus far, persons appear to be comfortable with their assignments; No need to reassign responsibilites, flex leader has valueable role | Closed | Chris
Technology competence | Not familiar with the framework used | Team member is not familiar with either React or Spring Boot | 2 | 4 | 4 | 32 | Design Leader/Configuration Leader | 2023-09-18 | Design leader to provide guidance on framework but also team members to reach out if they don't understand. Configuration leader to support. | Discuss architeture in meetings. Also devise plan to learn framework with team members who need guidance. Team members have taken up the challenge to learn the frameworks, with more experience team members offering support as needed | Closed | Andrew
| Not familiar with the programming language used | Team member is not familiar with Java or JavaScript. | 1 | 5 | 5 | 25 | All team members. | 2023-09-18 | Team members need to learn at least the basics of both Java and JavaScript. Not knowing the programming languages used will make learning the framework much more difficult. | Discuss in meetings team members ability and understanding and make sure if everyone is not comfortable with language they have plan to learn. | Open | Andrew
| Not familiar with unit testing | Team member has not done unit testing before. | 3 | 3 | 3 | 27 | QA Leader/Configuration Leader | 2023-10-18 | QA Leader to provide tests for application. Configuration leader to support. | Discuss in meetings tests needed for application. | Open | Andrew
| Other technology incompetence |  | 3 | 2 | 2 | 24 | Configuration Leader | 2023-10-18 | Address lack of technology understanding as it is introduced. | Discuss in meeting technologies to be used and plan for members to get comfortable with. | Open | Andrew
| Not familiar with Git |  | 2 | 1 | 4 | 80 | Configuration Leader | 2023-09-18 | Configuration leader to provide help with Git as needed. | Discuss in meeting understanding of Git for each member. | Open | Andrew
Design and implementation | Improper design | Improper design can lead to various problems, including usability issues, safety hazards, increased costs, and customer dissatisfaction. | 4 | 5 | 4 | 60 | various stakeholders | 2023-10-15 | Designers and engineers are at the forefront of ensuring proper design. They must have the necessary expertise and skills to create designs that meet functional requirements, safety standards, and user needs. | can achieve this by conducting thorough research, staying updated on best practices and ensuring that the design project stays on track. |  | Maryam
| Scalability Issues | As the application grows, it may face performance bottlenecks and scalability challenges. | 3 | 3 | 4 | 45 | Architect Leader | 2023-09-15 | Design the application with scalability in mind. Use load balancing, caching, and horizontal scaling techniques. | 1.Define Requirements and Goals:Identify the specific requirements of your application, including expected traffic, data volume, and performance goals. Determine thescalability goals, such as handling a certain number of concurrent users or transactions. 2. Choose the Right Architecture:Select an appropriate architecture that aligns with your scalability goals.
| improper technology stack | the selection and combination of software tools, programming languages, frameworks, libraries, and infrastructure components that are not well-suited for a particular software project. | 4 | 4 | 3 | 45 | Design Leader | 2023-09-15 | Begin by thoroughly understanding the project's objectives, functionality, scalability needs, performance requirements, security considerations, and any other specific requirements. | involving the stakeholders in the decision-making process can significantly reduce the risk of choosing an improper technology stack and increase the chances of a successful software project. |  | Maryam
| Messy code | "code smell," which is code poorly structured, hard to read, and challenging to maintain. Messy code can introduce a variety of issues and risks into our project, including reduced productivity, increased debugging time, and higher chances of introducing bugs. | 3 | 4 | 2 | 60 | various stakeholders | 2023-10-18 | By involving team members in reviewing each other's code, you can ensure that code quality standards are upheld and that code smells are identified and addressed before they become problematic. | Define clear guidelines and coding standards that all team members should follow. This includes formatting, naming conventions, and best practices. | TO Do | Maryam
Testing | Not enough testing | not having enough tests to cover all the methods/features implemented | 2 | 2 | 3 | 48 | QA leader and other members | 2023-10-18 | implement test methods to cover as many method/code as possible | no test needed to be implemented yet | open | Whitney
| incorrect manual testing | manually testing the application but did not know the correct expected result | 2 | 3 | 4 | 48 | QA leader and other members | 2023-10-19 | knowing what to expect when perform manual testings | no test needed to be implemented yet | open | Whitney
| incorrect automated unit testing | incorrect logic in test methods | 2 | 3 | 4 | 48 | QA leader and other members | 2023-10-20 | update logic in test methods and confirm expected results when run test cases | no test needed to be implemented yet | open | Whitney
| incorrect automated integration testing | incorrect logic in flow | 2 | 3 | 3 | 36 | QA leader and other members | 2023-10-21 | mock objects correctly for testing/ check flow | no test needed to be implemented yet | open | Whitney
Integration and deployment | Not enough time for integration and deployment | Team is still working on completing application and does not have time to deploy. | 4 | 2 | 5 | 40 | Configuration Leader | 2023-10-18 | Research deployment options like AWS/Heroku. | Discuss at end of development of application. | Open | Andrew
| Not enough available resources for server deployment | Application has been completed but techological roadblocks prevent deployment | 4 | 2 | 4 | 32 | Configuration Leader | 2023-10-18 | Configuration leader to research other options. | Discuss at end of development of application. | Open | Andrew
Security | Discover vulnerability in the code/third party software | weakness that could be exploited by malicious actors | 3 | 3 | 3 | 27 | Security leader and other members | 2023-10-17 | - setup controlled environment (test env that mirros the prod env) - code review (check for potential security flaws) - setup analysis tools to automate scanners to help identify common vulnerabilities | no security implementation needed to be implemented yet | open | Hanwen
Security | Insecure storage of user credentials | weak encryption that can lead to unauthorized access and user data breaches | 2 | 4 | 4 | 32 | Security leader and other members | 2023-10-17 | - find a reliable third party library that provides hash and salt passwords to make it harder for attackers to hack the password | no security implementation needed to be implemented yet | open | Hanwen
Security | Plaintext transmission of network traffic | security vulnerability occurs when sensitive data is transmmitted across a network in unencrypted form so that unprotected data packets might be potentially exploited to attackers | 1 | 3 | 2 | 30 | Security leader and other members | 2023-10-17 | - use encryption protocols like HTTPS - develop secure API with proper authentication and authorization mechanisms | no security implementation needed to be implemented yet | open | Hanwen